## DEC-JAN
DAILY REPORT (DEC-JAN 2023)
AMITHA RK
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2022-12-26 | MS123 | TD L05 SLAB UPDATION, CVG P1&P2 L3&4 UPDATION
2022-12-27 | MS123 | TD L06 POUR 10 SLAB B1,T1 |  |  | COMPLETED
2022-12-28 | MS123 | TD L06 POUR 10 SLAB B2,T2 |  |  | COMPLETED
2022-12-29 | MS123 | TD L06 POUR 10 SLAB BEAM SECTIONS & CHAIR |  |  | P10 SUBMITTED
2022-12-30 | CREST GRANDE | TB P06 SLAB B1, B2,T1 |  |  | COMPLETED
2022-12-31 | CREST GRANDE | TB P06 SLAB T2, OPENING ADDL SECTIONS BEAMS & CHAIR |  |  | COMPLETED
2023-01-01
2023-01-02 | CREST GRANDE | TB PO5 SLAB SUBMITTED FOR CHECKING
CVG L07 P1&P2 SLAB B2,T2,T1
2023-01-03 | CVG | CVG L07 P1& P2 BEAMS , DOWNSTAND & UPDATIONS AS PER NEW GA
CVG L03 P05 SLAB STARTED
2023-01-04 | CVG | CVG L07 UPDATIONS AS PER NEW GA & REINFORCEMENT
CVG L03 P05 SLAB MESH , BEAMS AND OTHER DETAILS
2023-01-05 | MS123 | TD L06 SLAB COMMENTS, CREST GRANDE GF BEAM
2023-01-06 | S TOWER | L53 RC SLAB B2,T2, T1, OPENING ADDL
2023-01-07 | S TOWER | L53 BEAMS SUBMITTED FOR CHECKING,
| CREST GRANDE | CG P05 L01 SLAB UPDATION MESH AS PER GA AND REINF.
| MS123 | TD P06 SLAB SUBMISSION | 35.68 | 4
2023-01-09 | CREST GRANDE | CG P05 SUBMISSION
|  | S TOWER L53 COMMENTS | 8.23 | 3 | SUBMITTED(FINAL SUBMISSION)
| MS123 | TD L7 SLAB TOP MESH T2 STARTED
2023-01-10 | MS123 | TD L7 SLAB TOP MESH |  |  | COMPLETED
| S TOWER | L53 SLAB SECONDARY CHECKING COMMENTS UPDATED |  |  | SUBMITTED
| CVG | L07 SLAB SUBMISSIO B2,T2,T1,BEAMS & DOWNSTAND | 25.22 | 3
2023-01-11 | CVG | L3&L04 P07 SLAB BOTTOM MESH, T1
2023-01-12 | CVG | L3&L04 P07 SLAB T2, OPENING, SUNKEN ADDL& DETAILS
| CG | L1 P05 UPDATION AS PER MEP & NEW CJ, PLACING BOOM
| CVG | L2MID SLAB P05 SUBMIISION | 22.53 | 4
2023-01-13 | CVG | L3&L04 P07 SLAB |  |  | SUBMITTED FOR PRIMARY CHECKING
| CG | L1 P06 SLAB COMMENTS, UPDATION AS PER GA , MEP, CJ TOP MESH
| MS 123 | TD P09 SLAB L07 SUBMIITED | 9.56 | 2 | SUBMITTED
2023-01-14 | CG | P05 SLAB COMMENTS(SITE) |  |  | SUBMITTED
|  | P06 SLAB COMMENTS MESH | 23.23 | 3 | SUBMITTED
| CVG | L05 P05 SLAB B1 |  |  | COMPLETED
2023-01-15
2023-01-16 | CVG | CVG L05 P04 SLAB TOPMESH , ADDL STARTED
| CG | CG L01 P05 & P06 SLAB UPDATION PUNCHING SHEAR
2023-01-17 | CVG | CVG L05 P04 TOP ADDL , BEAMS& CHAIR ,RC SLABS
2023-01-18 | CVG | CVG L05 P04 SLAB |  |  | SUBMITTED FOR CHECKING
2023-01-19 | MS123 | TD L08 P09 SLAB B1,T1,BEAMS & DETAILS |  |  | SUBMITTED FOR CHECKING
2023-01-20 | MS123 | CVG L03 P07 SLAB COMMENTS
|  | TD L08 COLUMN STARTER, TD L07 P10 SLAB MESH |  |  | SUBMITTED FOR CHECKING
2023-01-21 | MS123 | TD L07 P10 SLAB
2023-01-22 | CREST GRANDE | TC PILECAP COMMENTS |  |  | SUBMITTED
2023-01-23 | CREST GRANDE | TC &TA PILECAP UPDATIONS ,TB PILECAP UPDATION
| MS123 | TD L08 SLAB SUBMISSION | 18.02 | 2 | SUBMITTED
2023-01-24 | CVG | L08 P01&02 BOTTOM MESH, TOPADDL P2 |  |  | SUBMITTED FOR CHECKING
2023-01-25 | CREST GRANDE | TB PILECAP UPDATION |  |  | SUBMITTED
TB L2 P05 SLAB UPDATION (SCALE CHANGE)
| CVG | L08 SLAB SUBMISSION | 14.08 | 2
|  | TOTAL | 156.55 | 23

## JAN-FEB
DAILY REPORT (JAN - FEB 2023)
AMITHA
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2023-01-26
2023-01-27 | CVG | L8 TO L22 TYP SLAB UPDATION(SUNKEN TOP MESH) |  |  | SUBMITTED
| MS123 | TD SLAB COMMENTS(L7 P10) |  |  | SUBMITTED FOR SEC CHECKING
2023-01-28 | MS123 | TD L6 SWIMMING POOL SLAB |  |  | SUBMITTED FOR CHECKING
2023-01-29
2023-01-30 | MS123 | TD L6 SWIMMING POOL SLAB COMMENTS(PRIMARY) |  |  | SUBMITTED FOR SEC CHECKING
TD L6 SWIMMIMNG POOL BEAMS
2023-01-31 | MS123 | TD L6 SWIMMIMNG POOL BEAMS |  |  | COMPLETED
| CVG | L5 P03 SLAB T2
| MS123 | TD L6 SWIMMING POOL SLAB COMMENTS(SEC)
2023-02-01 | MS123 | TD L6 SWIMMING POOL SLAB COMMENTS(SEC) | 5.19 | 1 | SUBMITTED
| MS123 | TD L6 SWIMMING POOL SLAB UPSTND | 14.35 | 2
TD L6 P12 RAMP
2023-02-02 | MS123 | TD L7 P10 SLAB SUBMISSION(SEC COMMENTS) | 17.6 | 2 | SUBMITTED(FINAL)
|  | S TOWER ROOF SLAB SUBMISSION(SEC COMMENTS) |  |  | SUBMITTED(FINAL)
| CREST GRANDE | TB PART2 STARTER UPDATION(LINKS & GF TO L1 COMMNTS)
2023-02-03 | CREST GRANDE | TB PART2 STARTER UPDATION |  |  | SUBMITTED
| CVG | L5 P03 SLAB SECTIONS |  |  | SUBMITTED FOR CHECKING
| CREST GRANDE | L3 P05 SLAB T2 LAYER,SHEET SETTING | 9.424 | 2
| CVG | L3&L4 SLAB FINAL SUBMISSION P7 | 19.17 | 4
2023-02-04 | MS123 | TD L8 SWIMMING POOL PRIMARY COMMENTS |  |  | SUBMITTED FOR SE CHECKING
2023-02-05
2023-02-06 | MS123 | TD L8 SWIMMING POOL SLAB(SEC COMMENTS)(BEAMS) | 2.625 | 0.5 | COMPLETED
|  | TD L8 SWIMMING POOL UPSTAND |  |  | COMPLETED
2023-02-07 | CVG | L5 POUR 4 PRIMARY COMMENTS |  |  | SUBMITTED FOR SE CHECKING
| MS123 | TD L6 UPSTAND COMMENTS |  |  | SUBMITTED FOR SE CHECKING
2023-02-08 | CREST GRANDE | L5 P06 B1 T1 | 8.59 | 2 | SUBMITTED FOR CHECKING
| MS123 | TD L6 UPSTAND COMMENTS (SEC) | 9.72 | 1.5 | SUBMITTED (FINAL)
| MS123 | TB L39 SLAB B1
2023-02-09 | MS123 | TB L39 SLAB T1, SHEET SETTING | 19.17 | 3 | SUBMITTED FOR CHECKING
| MS123 | TD UPSTANDS UPDATION |  |  | SUBMITTED
2023-02-10 | MS123 | TD L8 TO SWIMMIMNG POOL LEVEL COLUMNS & WALLS |  |  | SUBMITTED FOR CHECKING
| CVG | L6 BEAM
2023-02-11 | MS123 | TB L39 SLAB PRIMARY COMMENTS |  |  | SUBMITTED FOR SE CHECKING
| S TOWER | TC CLOSING SLAB |  |  | SUBMITTED FOR CHECKING
| MS123 | BMU LEVEL BEAMS |  |  | STARTED
2023-02-12
2023-02-13 | SUBSATION | FOOTING , COLUMN & ROOF SLAB | 2.214 | 1 | SUBMITTED FOR CHECKING
| S TOWER | TC2 & HOIST 01 GF TO L01
2023-02-14 | S TOWER | TC2 & HOIST 01 GF TO L01 |  |  | SUBMITTED FOR CHECKING
| CVG | L5 P06 SLAB PRIMARY COMMENTS
2023-02-15 | S TOWER | TC2 & HOIST 01 GF TO L01 |  |  | SUBMITTED FOR SE CHECKING
| CVG | L8-22 TYPICAL SLAB CONSULTANT COMMENTS & CJ UPDATION |  |  | SUBMITTED
| CVG | TOWER CRANE TIE BACK ADDITIONAL | 4.74 |  | SUBMITTED
2023-02-16 | CREST GRANDE | L6 P06 SLAB B1, B2
| S TOWER | TOWER CRANE CLOSING SUBMISSION | 5.439 | 3 | SUBMITTED
2023-02-17 | CREST GRANDE | L6 P06 SLAB T1
| CREST GRANDE | L05 P05 CJ UPDATION |  |  | SUBMITTED
| CVG | L8-L22 SLAB T2 LAYER UPDATION |  |  | SUBMITTED
2023-02-18 | MS123 | TD L8 TO SWIMMIMNG POOL LEVEL COLUMNS & WALLS SEC COMMENTS | 11.099 | 2.5 | SUBMITTED(FINAL)
| CREST GRANDE | L6 P06 SLAB T2, PUNCHING SHEAR
| CVG | L05 P04 SLAB | 40 | 3
2023-02-19
2023-02-20 | CREST GRANDE | L6 P06 SLABOPENING ADDL , SECTION &DETAILS
| MS123 | TD L8 SWIMMIMNG POOL UPSTAND UPDATION
2023-02-21 | CREST GRANDE | L6 P06 SLAB UPDATION AS PER NEW GA |  |  | SUBMITTED FOR CHECKING
| MS123 | TD L8 STAIR UPDATION
2023-02-22 | S TOWER | BASEMENT ZONE 6&7 SLAB AND STAIR |  |  | SUBMITTED FOR CHECKING
2023-02-23 | DAMAC HILLS | G8 VILLA 9A1 BEAMS & SECTIONS |  |  | SUBMITTED FOR CHECKING
2023-02-24 | S TOWER | ROOF LEVEL PARAPET DETAILS |  |  | SUBMITTED FOR CHECKING
| S TOWER | BASEMENT ZONE 6&7 SLAB AND STAIR(PRIMARY & SEC COMMENTS) | 5.269 | 2 | SUBMITTED(FINAL)
2023-02-25 | DAMAC HILLS | G8 VILLA 9A1 BEAMS & SECTIONS |  |  | SUBMITTED(FINAL)
| CVG | L6 P04 COMMENTS PRIMARY
|  | TOTAL | 174.6 | 29.5

## FEB-MAR
DAILY REPORT (FEB - MAR 2023)
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2023-02-26
2023-02-27 | S TOWER | ROOF LEVEL UPSTANDS(PRI& SEC COMMENTS) | 2.136 | 1 | SUBMITTED(FINAL)
B1 ZONE 6&7 RAMP WALL STARTER
|  | CVG L5 P03 SLAB SUBMISSION T2 | 4.78 | 0.5
|  | CVG L5 SALB BEAMS | 1.77 | 0.25
|  | G8 BEAMS SUBMISSION | 2.77 | 1.5
2023-02-28 | S TOWER | ROOF LEVEL SWIMMIMNG POOL WALLS(REVISED) |  |  | SUBMITTED
| HEBIAH SUBSTATION | RAFT FOUNDATION B1 LAYER |  |  | SUBMITTED FOR CHECKING
2023-03-01 | HEBIAH SUBSTATION | RAFT FOUNDATION T1 LAYER, TOP ADDL, TRENCH WALLS7 STAIR STARTERS |  |  | SUBMITTED FOR CHECKING
2023-03-02 | HEBIAH SUBSTATION | B4 ADDL ,RAFT FOUNDATION SUBMISSION | 71.07 | 4.5 | SUBMITTED(FINAL)
2023-03-03 | HEBIAH SUBSTATION | RETAINING WALL STARTERS (VERTICAL) | 9.039 | 1.5
2023-03-04
2023-03-05
2023-03-06 | MS123 | TB ROOF PLINTH REINF. DETAILS | 1.95 | 1 | SUBMITTED(FINAL)
|  | BMU LEVEL BEAMS | 0.423 | 0.25
| CREST GRANDE | TB L06 P06 SLAB | 24.3 | 5.5 | SUBMITTED(FINAL)
2023-03-07 | CREST GRANDE | TB L07 P05 SLAB B1,B2,T2
2023-03-08
2023-03-09 | CREST GRANDE | TB L07 P05 SLAB |  |  | SUBMITTED FOR CHECKING
2023-03-10 | CREST GRANDE | TA PILCAP & STARTER UPDATION
2023-03-11 | CREST GRANDE | TC PILCAP & STARTER UPDATION
2023-03-12
2023-03-13 | CREST GRANDE | TB L07 P06 SLAB MESH &OPENING ADDL | 16.58 | 5
2023-03-14 | S TOWER | BASEMENT ZONE 6 &7 RAMP WALL |  |  | SUBMITTED FOR CHECKING
2023-03-15 | CREST GRANDE | TB L07 P05 SLAB SUBMISSION(PRI&SEC COMMENTS) | 25.73 | 6 | SUBMITTED
| CREST GRANDE | TB L07 P06 SLAB SECTIONS&DETAILS |  |  | SUBMITTED FOR CHECKING
2023-03-16 | S TOWER | BASEMENT ZONE 6 &7 RAMP WALL COMMENTS | 3.469 | 2 | SUBMITTED
| CVG | L5 P04 SLAB UPDATION(AS PER NEW CJ) |  |  | SUBMITTED
2023-03-17 | CVG | L5 P04 UPSTAND & SWIMMIMNG POOLWALLS |  |  | SUBMITTED FOR CHECKING
2023-03-18 | CVG | L5 P04 UPSTAND & SWIMMIMNG POOLWALLS(updation as per new arch) |  |  | SUBMITTED FOR CHECKING
2023-03-19
2023-03-20 | CVG | L5 P04 UPSTAND & SWIMMIMNG POOLWALLS COMMENTS | 20.314 | 4 | SUBMITTED
| MS123 | TA ROOF LEVEL PLINTH REINF DETAILS | 1.1315 | 0.5 | SUBMITTED
2023-03-21 | CVG | L05 P03,06&05 UPSTAND AND PLANTER WALLS |  |  | SUBMITTED FOR CHECKING
2023-03-22 | CVG | L05 P03,06&05 UPSTAND AND PLANTER WALLS COMMENTS |  |  | SUBMITTED FOR SEC CHECKING
| CREST GRANDE | TB L07 P05&P06 CJ UPDATION |  |  | SUBMITTED
| CVH | PART-01& 02 PILECAP & STARTERS |  |  | STARTED
2023-03-23 | CVG | L05 P03,06&05 UPSTAND AND PLANTER WALLS COMMENTS | 26.22 | 3 | SUBMITTED
| DAMAC HILLS | G4 & G8 VILLA SOG |  |  | SUBMITTED FOR CHECKING
| ARABIAN RANGES | PART-01 FOUNDATION COMMENTS |  |  | SUBMITTED
2023-03-24 | DAMAC HILLS | G4 & G8 &G 6 VILLA SOG COMMENTS | 8.963 | 3 | SUBMITTED
| CVG | L05 P04 PLANTER WALL SITE COMMENTS |  |  | SUBMITTED
| CVH | PART-01& 02 PILECAP & STARTERS
2023-03-25 | CVH | PART-01& 02 PILECAP & STARTERS
| CG | L06 P06 SLAB CONSULTANT COMMENTS |  |  | SUBMITTED
2023-03-26
2023-03-27
|  | TOTAL | 220.6455 | 39.5

## MAR-APR
DAILY REPORT (MAR-APR 2023)
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2023-03-26
2023-03-27 | DAMAC HILLS | G4 VILLA 6 FF SLAB | 9.975 | 3.5
2023-03-28
2023-03-29 | CREST CRANDE | TB L07 SLAB P05 COMMENTS |  |  | SUBMITTED
| S TOWER | MANHOLE REINF DETAILS |  |  | SUBMITTED FOR CHECKING
2023-03-30 | CREST CRANDE | TB GF TO L01 RAMP SLAB |  |  | COMPLETED
2023-03-31 | MS123 | TA BMU LEVEL BEAMS UPDATION |  |  | SUBMITTED
2023-04-01 | S TOWER | WATER FEATURE
2023-04-02
2023-04-03 | CREST GRANDE | L07 TYP FLOOR SLAB P06 SITE COMMENTS |  |  | SUBMITTED
| CVG | L02 P07 SLAB UPDATION AS PER SUNKEN
2023-04-04 | CREST GRANDE | L01 TO L02 RAMP SLAB
| MS123 | TA BMU LEVEL BEAMS UPDATION |  |  | SUBMITTED
2023-04-05 | CREST GRANDE | L01 TO L02 RAMP SLAB |  |  | SUBMITTED FOR CHECKING
2023-04-06 | CREST GRANDE | L02 TO L03 RAMP SLAB
| CVG | L02 P07 SITE COMMENTS |  |  | SUBMITTED
| CREST GRANDE | TYPICAL FLOOR P05 CONSULTANT COMMENT |  |  | SUBMITTED
2023-04-07 | CVG | L05 P04,P3,5,5 UPSTAND SAND WALLS SITE COMMENT |  |  | SUBMITTED
| CREST GRANDE | L02 TO L03 RAMP SLAB |  |  | COMPLETED
2023-04-08 | CREST GRANDE | L03 TO L04 RAMP SLAB |  |  | COMPLETED
| CVG | L06 P03 SLAB SITE COMMENTS |  |  | SUBMITTED
2023-04-09
2023-04-10
2023-04-11 | CREST GRANDE | L14 SLAB P05 MESH
2023-04-12 | CREST GRANDE | L14 SLAB P05 ADDLS & DETAILS
2023-04-13 | CREST GRANDE | L14 SLAB P05 PUNCHING SHEAR 7 SECTIONS |  |  | SUBMITTED FOR CHECKING
| MS123 | TC POUR9A SLAB LEVEL 8
2023-04-14 | MS123 | TC POUR9A SLAB LEVEL 8
| DAMAC HILLS | G8 VILLA 9A1 ROOF SLAB OPENING & COLUMN STARTER
2023-04-15
2023-04-16
2023-04-17 | S TOWER | RAMP SLAB THICKENING |  |  | SUBMITTED FOR CHECKING
| CREST GRANDE | L14 P05 SLAB PRI COMMENTS |  |  | SUBMITTED FOR SEC CHECKING
| CREST GRANDE | L15-L17 P05 LAB |  |  | STARTED
2023-04-18 | CVH | PC149 COMMENTS (UPDATION) |  |  | SUBMITTED
| CREST GRANDE | L15-L17 P05 LAB |  |  | SUBMITTED FOR CHECKING
| DAMAC HILLS | G3 VILLA 5A2 UPDATION |  |  | SUBMITTED
2023-04-19 | DAMAC HILLS | G3 VILLA 5A2 PERGOLA DETAILS UPDATION |  | 1 | SUBMITTED
|  | G6 VILLLA 7A2 FF SLAB UPDATION |  |  | STARTED
| CVH | PART-01& 02 PILE CAPS | 41.428 | 4
2023-04-20 | S TOWER | RAMP SLAB THICKENING COMMENTS | 2.782 | 1 | SUBMITTED
| DAMAC HILLS | G4 VILLA 6 PERGOLA BEAMS |  | 1 | SUBMITTED
| CVG | L23 MID SLAB & BEAM UPDATION |  |  | SUBMITTED
2023-04-21 | CVG | L23 LEVEL UPSTAND & PLINTH |  |  | SUBMITTED FOR CHECKING
| MS123 | TC POUR9A SLAB LEVEL 8 | 6.014 | 2 | SUBMITTED
2023-04-22
2023-04-23
2023-04-24 | CVG | L2 POUR 7 SLAB TC & BEAM UPDATION |  |  | SUBMITTED
| CREST GRANDE | L14 POUR-01 SLAB UPDATION AS PER NEW GA & REINF |  |  | SUBMITTED FOR FOR SEC CHECKING
2023-04-25 | CREST GRANDE | L14 SLAB POUR-01 SEC COMMENTS | 30.168 | 8 | SUBMITTED
| CREST GRANDE | L15-17 P-01 SLAB PRIMARY COMMENTS |  |  | SUBMITTED FOR FOR SEC CHECKING
|  | TOTAL | 90.367 | 20.5

## APR-MAY
DAILY REPORT (APR - MAY 2023)
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2023-04-26 | CREST GRANDE | L15-L17 POUR-01 SLAB TB SEC COMMENTS | 29.991 | 9 | SUBMITTED
| CVG | L23 UPSTAND AND PLINTH REINF COMMENTS
| CREST GRANDE | RAMP FROM L4 TO L5 |  |  | COMPLETED
2023-04-27 | CVG | L23 MID SLAB & BEAM UPDATION(SITE COMMENTS) |  |  | SUBMITTED
| CVG | L23 UPSTAND AND PLINTH REINF UPDATION |  |  | SUBMITTED
| CREST GRANDE | L19-36 SLAB POUR-01 SLAB
2023-04-28 | CVG | L23 MID SLAB & BEAM UPDATION(SITE COMMENTS) |  |  | SUBMITTED
| CVG | L23 UPSTAND AND PLINTH REINF UPDATION |  |  | SUBMITTED
| CREST GRANDE | TC PILECAP UPDATION AS PER TA COMMENTS |  |  | SUBMITTED
| CREST GRANDE | L19-24 & L27-L36 SLAB POUR-01 |  |  | SUBMITTED FOR CHECKING
2023-04-29 | CREST GRANDE | RAMP SLAB SHEET ADJUSTMENT |  |  | NOT COMPLETED
| AL ASHRAM | TW2 CORE WALL FROM L2 TO L3
2023-04-30 | AL ASHRAM | TW2 CORE WALL FROM L2 TO L3 VERTICALS & ELEVATION,
2023-05-01 | AL ASHRAM | TW2 CORE WALL FROM L2 TO L3 VERTICALS & ELEVATION, |  |  | SUBMITTED FOR CHECKING
2023-05-02 | AL ASHRAM | TW2 CORE WALL FROM L2 TO L3 COMMENTS | 16.384 | 1.5 | SUBMITTED
| AL ASHRAM | TW2 CORE WALL FROM L3 TO L5 | 16.384 | 1.5 | SUBMITTED
| G2 INTERNATIONAL | FF RC SLAB & BEAMS
2023-05-03 | G2 INTERNATIONAL | FF RC SLAB & BEAMS COMMENTS&SECTIONS B20 | 45.12 | 4 | SUBMITTED FOR CHECKING
| CVG | L23 MID SLAB & BEAM SITE COMMENTS |  |  | SUBMITTED
2023-05-04 | MS123 | RMU ROOM DETAIL |  |  | SUBMITTED FOR CHECKING
| G2 INTERNATIONAL | FF PART-01 SLAB COVER UPDATION |  |  | SUBMITTED
2023-05-05 | MS123 | RMU ROOM DETAIL COMMENTS | 4.8 | 2 | SUBMITTED
| G2 INTERNATIONAL | B-05 FF SLAB SECTIONS & DETAILS | 5.644 | 1 | SUBMITTED
2023-05-06
2023-05-07 | DAMAC HILLS | G2 VILLA 5A1 | 13.188 | 4 | 80% COMPLETED
2023-05-08 | CREST GRANDE | L14 SITE COMMENTS POUR-01 |  |  | SUBMITTED
| G2 INTERNATIONAL | NG6 VILLA TIE BEAMS & SECTIONS |  |  | SUBMITTED
2023-05-09 | STOWER | MANHOLE REINFORCEMNET DETAILS | 1.251 | 2 | SUBMITTED
| G2 INTERNATIONAL | NG6 VILLA TIE BEAM UPDATION |  |  | SUBMITTED
| G2 INTERNATIONAL | BUILDING 20 FF PART 2 UPDATION AS PER PART01 COMMENTS |  |  | SUBMITTED
2023-05-10 | CREST GRANDE | L14 SITE COMMENTS POUR-02 |  |  | SUBMITTED
| CREST GRANDE | TC PILECAP SITE COMMENTS |  |  | SUBMITTED
| G2 INTERNATIONAL | NG6 VILLA FF SLAB | 4.522 | 1
2023-05-11 | G2 INTERNATIONAL | NG6 VILLA FF SLAB, PERGOLA BEAMS
2023-05-12 | G2 INTERNATIONAL | NG6 VILLA PERGOLA BEAMS |  |  | SUBMITTED FOR CHECKING
| G2 INTERNATIONAL | BUILDING 20 PART 2 UPDATION(AS PER COMMENTS) |  |  | SUBMITTED
2023-05-13 | CVH | PILECAP & STARTER UPDATION
| CVG | L05 P05 SLAB SITE COMMENTS |  |  | SUBMITTED
2023-05-14
2023-05-15 | G2 INTERNATIONAL | NG6 VILLA PERGOLA BEAMS | 4.31 | 2 | SUBMITTED
| CVG | TRENCH REINF DETAILS | 6.424 | 1 | SUBMITTED
| CVH | PILECAP & STARTER UPDATION(AS PER LATEST DESIGN) |  |  | SUBMITTED
2023-05-16
2023-05-17 | CVH | PC149 PILECAP UPDATION(AS PER LATEST DESIGN) |  |  | SUBMITTED
| G2 INTERNATIONAL | NG8 VILLA GF SECTIONS & BEAMS | 4.188 | 2 | SUBMITTED
2023-05-18 | CRESTGRANDE | L15-L17 POUR 01 SLAB SITE COMMENTS |  |  | SUBMITTED
| G2 INTERNATIONAL | NG8 VILLA SFSLAB B1,B2 LAYER
| CRESTGRANDE | L19-24 & L27-36 SLAB POUR-01 PRI COMMENTS
2023-05-19 | CRESTGRANDE | L19-24 & L27-36 SLAB POUR-01 PRI COMMENTS | 30.273 | 9 | SUBMITTED
| MS123 | WATER TANK PLINTH BBS |  |  | SUBMITTED
| G2 INTERNATIONAL | NG8 VILLA SFSLAB ADDLS& BEAMS | 11.411 | 3 | SUBMITTED FOR CHECKING
| CVH | PC149 PILECAP COMMENTS |  |  | SUBMITTED
2023-05-20 | G2 INTERNATIONAL | BUILDING 20 L02 SLAB & BEAMS
| G2 INTERNATIONAL | NG8 VILLA FF PERGOLA BEAMS |  |  | SUBMITTED
2023-05-21
2023-05-22 | G2 INTERNATIONAL | BUILDING 20 L02 SLAB & BEAMS
| CRESTGRANDE | L14 PART 02 CONSULTANT COMMENTS |  |  | SUBMITTED
2023-05-23 | G2 INTERNATIONAL | BUILDING 20 L02 SLAB & BEAMS | 17.77 | 3.25 | SUBMITTED
| CVH | PILECAP & STARTERS COMMENT UPDATION
2023-05-24 | CVH | PILECAP & STARTERS COMMENT UPDATION
2023-05-25 | G2 INTERNATIONAL | NG8 VILLA FF PERGOLA BEAMS COMMENTS | 5.7 | 2 | SUBMITTED
| CVH | PILECAP & STARTERS COMMENT UPDATION |  |  | SUBMITTED
2023-05-26 | G2 INTERNATIONAL | BUILDING 20 LEVEL 2 SLAB & BEAM UPDATION (AS PER COMMENTS) |  |  | SUBMITTED
| CREST GRANDE | GF TO L1 RAMP SLAB |  |  | STARTED
2023-05-27 | CREST GRANDE | GF TO L1 RAMP SLAB
2023-05-29 | CREST GRANDE | GF TO L1 RAMP SLAB
| G2 INTERNATIONAL | BUILDING 5 SLAB L05 BOTTOM INTEGRITY AND SETTING | 6.149 | 1
| CVG | L04 P04 SITE COMMENTS |  |  | COMMENTS COMPLETED
2023-05-30 | CREST GRANDE | GF TO L1 RAMP SLAB
2023-05-31 | SUNDAY
|  | TOTAL | 223.509 | 49.25

## MAY-JUN
DAILY REPORT (MAY - JUNE 2023)
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2023-06-01 | CREST GRANDE | GF TO L1 RAMP SLAB |  |  | SUBMITTED FOR CHECKING
| G2 INTERNATIONAL | BUILDING 5 SLAB & BEAM COMMENTS(PRIMARY) | 2.85 | 0.5 | SUBMITTED FOR CHECKING
2023-06-02 | AL ASHRAM | TOWER L01 SLAB MESH & PAN BOX DETAILS | 1.72 | 0.5
| CREST GRANDE | GF TO L1 RAMP SLAB COMMENTS | 22.262 | 3
2023-06-03 | CREST GRANDE | L1 TO L2 RAMP SLAB & BEAMS
2023-06-04 | SUNDAY
2023-06-05 | CREST GRANDE | L1 TO L2 RAMP SLAB & BEAMS
| MS123 | TD LEVEL 6 ADDITIONL ROOM | 2.49 | 1 | SUBMISSION
2023-06-06 | CREST GRANDE | L1 TO L2 RAMP SLAB & BEAMS COMMENTS & SUBMISSION | 26.142 | 3 | SUBMISSION
| CVH | TA PILECAP 168 MESH |  |  | STARTED
2023-06-07 | CVH | TA PILECAP 168 MESH |  |  | BOTTOM MESH COMPLETED
2023-06-08 | CVH | TA PILECAP 168 TOP MESH & DETAILS |  |  | SUBMITTED FOR CHECKING
2023-06-09 | TOWN HOUSE | GF SLAB T1 LAYER |  |  | 50% COMPLETED
2023-06-10 | TOWN HOUSE | GF SLAB T1 LAYER
2023-06-11 | SUNDAY
2023-06-12 | CREST GRANDE | LEVEL 23 POUR 02 SLAB | 30.445 | 8 | SUBMITTED
| CREST GRANDE | WATER TANK RAFT UPDATION |  |  | SUBMITTED
2023-06-13 | CVH | PILECAP PC168 COMMENTS & SUBMISSION | 431.505 | 4.5 | SUBMITTED
2023-06-14 | CHEDI | TRENCH UPDATION |  |  | UPDATED & SUBMITTED
| CREST GRANDE | L25 & 26 SLAB POUR-01
2023-06-15 | CREST GRANDE | L25 & 26 SLAB POUR-01 | 31.5 | 9 | SUBMITTED
2023-06-16 | CVH | TB PART 1&2 PILECAP & STARTER UPDATION |  |  | UPDATED AND SUBMITTED
2023-06-17 | TOWN HOUSE | GF SLAB T2 LAYER COMMENTS | 12.75 | 1.25 | SUBMITTED
2023-06-18 | SUNDAY
2023-06-19 | CVH | TB PC149 CONSULTANT COMMENTS |  |  | REVISED AND SUBMITTED
| ALASHRAM | LEVEL 02 SLAB MESH AND SECTIONS |  |  | SUBMITTED
2023-06-20 | CVH | PILECAP & INDIVITUAL PILECAP UPDATION |  |  | SUBMITTED
2023-06-21 | G2 INTERNATIONAL | LEVEL 7 PART 1 SLAB & BEAM
| SHOBHA HARTLAND | TYPE A VILLA FOUNDATION B1 TI |  |  | COMPLETED
2023-06-22 | SHOBHA HARTLAND | TYPE A VILLA FOUNDATION PLINTH WALL |  |  | COMPLETED
| CREST GRANDE | TB PART 2 FOUNDATION TRENCH
2023-06-23 | CREST GRANDE | TB PART 2 FOUNDATION TRENCH |  |  | SUBMITTED FOR CHECKING
| CREST GRANDE | TB WATER TANK INDIVITUAL PILECAP COMMENTS(SITE) |  |  | SUBMITTED
2023-06-24 | CREST GRANDE | TB PART 2 FOUNDATION TRENCH COMMENTS | 21.46 | 2 | SUBMITTED
2023-06-25 | SUNDAY
2023-06-26 | CREST GRANDE | WATER TANK RAFT UPDATION AS PER LATEST IFC |  |  | SUBMITTED
| CVH | TC3 TOWER CRANE FOUNDATION REINFORCEMENT DETAILS | 4.08 | 1 | SUBMITTED
2023-06-27 | ALASHRAM | TOWER L6-9 SLAB SUBMISSION | 21.52 | 7 | SUBMITTED
|  | TOWER L16-18 SLAB SUBMISSION | 21.53 | 7
2023-06-28 | CVH | TA PILECAP & STARTERS & TIE BEAMS
2023-06-29 | HOLIDAY
2023-06-29 | CVH | TA PILECAP & STARTERS
|  | WATER TANK TOP COVER SLAB UPDATION |  |  | SUBMITTED FOR CHECKING
2023-06-30 |  | TA PILECAP & STARTERS |  |  | SUBMITTED FOR CHECKING
|  | TOTAL | 630.254 | 47.75

## JUN-JULY
DAILY REPORT (JUNE -JULY 2023)
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2023-07-01 | CREST GRANDE | CREST GRANDE RAMP SLAB L02 TO L04
2023-07-02 | SUNDAY
2023-07-03 | CREST GRANDE | CREST GRANDE RAMP SLAB L02 TO L04 |  |  | SUBMITTED FOR CHECKING
2023-07-04 | CVH | TA PILECAP & STARTER & TIE BEAM PRI COMMENTS |  |  | SUBMITTED FOR SEC CHECKING
| CREST GRANDE | RAMP L02 TO L04 SEC COMMENTS | 23.7 | 5 | SUBMITTED
2023-07-05 | CVH | TA PILECAP & STARTER & TIE BEAM SEC COMMENTS | 34.51 | 6 | SUBMITTED
2023-07-06 | LEAVE
2023-07-07
2023-07-08 | ARABIAN RANCHES | PART 3 SLAB LEVEL 01 |  |  | SLAB COMPLETED
2023-07-09 | SUNDAY
2023-07-10 | ARABIAN RANCHES | PART 3 SLAB & BEAMS LEVEL 01 |  |  | COMPLETED
2023-07-11 | ARABIAN RANCHES | PART 3 BEAMS LEVEL 01
2023-07-12 | ARABIAN RANCHES | PART 2 B1 LAYER |  |  | 60% done
| AL ASHRAM | TOWN HOUSE GF BEAM UPDATION AS PER COMMENTS
2023-07-13 | AL ASHRAM | TOWN HOUSE GF BEAM UPDATION AS PER COMMENTS |  |  | Updated and submitted
| CREST GRANDE | WATER TANK RAFT UPDATION AS PER PLACING BOOM |  |  | Updated and submitted
| ARABIAN RANCHES | PART 1 BEAM COMMENTS 2 SHTS
2023-07-14 | CREST GRANDE | PART 2 PILECAP & STARTER CONSULTANT COMMENTS
| CREST GRANDE | WATER TANK TOP COVER SLAB UPDATION FOR PLACING BOOM
2023-07-15 | ARABIAN RANCHES | PART 3 PT SLAB AND IT'S DETAILS
2023-07-16 | SUNDAY
2023-07-17 | ARABIAN RANCHES | PART 3 SLAB AND BEAM COMMENTS AND AUBMISSION | 46.06 | 8 | SUBMITTED
2023-07-18 | CVH | TA PILECAP PC168 UPDATION |  |  | WAITING FOR CAD FILE (ADDL)
| CVH | INDIVIDUAL PILECAP & STARTER UPDATION AS PER LATEST ADVANCE COPY
2023-07-19 | CVH | INDIVIDUAL PILECAP & STARTER UPDATION AS PER LATEST ADVANCE COPY
| CREST GRANDE | WATER TANK RAFT UPDATION +CONSULTANT COMMENTS
2023-07-20 | CVH | TA PILECAP PC 168 UPDATION
| WATER PARK | AQUA TWIST WALL |  |  | PENDING WAITING FOR RFI
| SHOBHA HARTLAND | TYPE A FOUNDATION | 3.875 | 2.5
2023-07-21 | CVH | INDIVIDUAL PILECAP & STARTER COMMENTS(SIR) |  |  | SUBMITTED
|  | TA PILECAP PC 168 COMMENTS |  |  | SUBMITTED
2023-07-22 | WATER PARK | BRIDGE 01 FOUNDATION |  |  | SUBMITTED FOR CHECKING
2023-07-23 | SUNDAY
2023-07-24 | WATER PARK | BRIDGE 02 FOUNDATION DETAILS |  |  | SUBMITTED FOR CHECKING
| AL ASHRAM | L11-14, L15, L16-18, L19 PULLOUT REINF DETAILS | 2.2 | 2
2023-07-25 | WATER PARK | BRIDGE 03 FOUNDATION DETAILS |  |  | 50% COMPLETED
2023-07-26 | WATER PARK | BRIDGE 03 FOUNDATION DETAILS
2023-07-27 | CVH | TB JUMP 03 COREWALLS AND SHEAR WALLS | 12.285 | 1.5 | SUBMITTED FOR CHECKING
2023-07-28 | AFAQ | BRIDGE 01 REINF DETAILS |  |  | SUBMITTED FOR CHECKING
| DAMAC HILLS | PG8 villa FF SLAB CONSULTANT COMMENTS
2023-07-29 | DAMAC HILLS | PG8 villa FF SLAB CONSULTANT COMMENTS
2023-07-30 | SUNDAY
2023-07-31 | DAMAC HILLS | PG8 villa FF SLAB CONSULTANT COMMENTS |  |  | SUBMITTED
|  | TOTAL | 122.63 | 25

## AUG
DAILY REPORT (JULY - AUG 2023)
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2023-08-01 | AFAQ | BRIDGE 01 FOUNDATION AND GL COMMENTS | 3.93 | 2
|  | BRIDGE 02 FOUNDATION AND GROUND LEVEL |  |  | submitted for checking
2023-08-02 | HALA | WATER TANK WALL FOUNDATION TO GF | 9.17 | 3 | submitted for checking
2023-08-03 | HALA | GROUND FLOOR TIE BEAMS |  |  | submitted for checking
| CREST GRANDE | PART 2 TRENCH UPDATION |  |  | submitted
2023-08-04 | CVH | TB PILECAP PC 149 UPDATION (SUMP PIT AND STAIR STARTER) |  |  | submitted
2023-08-05 | CREST GRANDE | GRADE BEAM UPDATION BASED ON IFC. |  |  | submitted
| AFAQ | BRIDGE 3 REINFORCEMWNT DETAILS |  |  | submitted for checking
2023-08-06
2023-08-07 | CVH | PILECAP POUR 7 SHEET SETTING AND UPDATIONGRADE
| ARABIAN RANCHES | LEVEL 01 SLAB ADDL UPDATION
2023-08-08 | ARABIAN RANCHES | LEVEL 01 SLAB ADDL UPDATION
| CVH | POUR 8 PILECAP |  |  | submitted for checking
| CVH | PODIUM POUR 6 PILECAP | 10.884 | 3 | submitted
2023-08-09 | NEW PROJECT | MIXED USE BUILDING LOWER RAFT SECTIONS AND SF | 40.994 | 1 | submitted for checking
2023-08-10 | CREST GRANDE | TB PART 2 PILECAP SITE COMMENTS |  |  | submitted
| CVG. | LEVEL 41 SLAB COMMENTS | 7.49 | 1 | completed
2023-08-11 | CVH | TA PODIUM PILECAP AND TIEBEAM CHECKING DRWG WITH LATEST DM APPVD DESIGN
|  | PODIUM POUR6 TIE BEAM PULLOUT AND COMMENTS |  |  | submitted
2023-08-12
2023-08-13
2023-08-14 | SHOBHA HARTLAND | TYPE C VILLA FOUNDATION SUBMISSION | 4.156 | 2 | SUBMITTED
2023-08-15
2023-08-16 | CVH | PODIUM POUR 07 PILE CAP & STARTER | 1.99 | 1 | SUBMITTED
| SHOBHA HARTLAND | TYPE B FOUNDATION | 2.325 | 2
2023-08-17
2023-08-18 | AFAQ | AQUATWIST PUMP ROOM SUBMISSION | 16.475 | 2
2023-08-19 | MIXED USE BUILDING | UPPER RAFT REINF DETAILS B1 T1 SECTIONS | 161.32 | 4
2023-08-20
2023-08-21 | AFAQ | AQUATWIST PUMP ROOM UPDATION BASED ON LATEST IFC |  |  | SUBMITTED
| AFAQ | BRIDGE 2 SUBMISSION | 1.065 | 2
2023-08-22 | CVH | TA PODIUM PILECAP AND TIEBEAM SITE COMMENTS |  |  | SUBMITTED
2023-08-23 | CVH | TA JUMP 4 FROM CJ BETWEEN GF AND L01
| CREST GRANDE | PART 2 PILECAP UPDATION |  |  | SUBMITTED
| SHOBHA HARTLAND | TA BKUNDARY WALL | 4.21 | 2
2023-08-24 | CVH | TA JUMP 4 GF CJ TO CJ BETWEEN GF AND L01 | 34.965 | 6
2023-08-25 | CVG | L42 TO 43 JUMP 02 ACS | 6.26 | 2 | SUBMITTED FOR CHECKING
2023-07-26 |  | L43 SLAB |  |  | STARTED
2023-07-27
2023-07-28 | SHOBHA ONE | PILECAP PC 103 |  |  | COMPLETED
2023-07-29
2023-07-30 | SHOBHA ONE | PILECAP PC103 |  |  | SUBMITTED FOR CHECKING
|  | PILECAP PC 70A |  |  | 80% COMPLETED
2023-07-31 | SHOBHA ONE | PILECAP PC 70A |  |  | SUBMITTED FOR CHECKING
| SHOBHA VERDE | FOUNDATION |  |  | J
JUST STARTED
|  | TOTAL | 305.234 | 33

## SEPT
DAILY REPORT (AUG - SEPT 2023)
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2023-09-01 | G+1VILLA | UNDER GROUND WATER TANK WALL REINF DETAILS | 1.411 | 1 | SUBMITTED
| SHOBHA VERDE | WATER TANK AND PUMP ROOM FOUNDATION B1 &B2
2023-09-02 | SHOBHA VERDE | WATER TANK AND PUMP ROOM FOUNDATION |  |  | 50% COMPLETED
2023-09-03 | SUNDAY
2023-09-04 | AL BARSHA | TOWER B L1 TO L2 LIFT AND STAIR WALL | 8.78 | 1 | SUBMITTED
| CVG | L35 TO 36 JUMP 4 CHECKING
| CREST GRANDE | L37 POUR 2 SLAB B1 LAYER |  |  | 60%COMPLETED
2023-09-05 | SHOBHA VERDE | WATER TANK AND PUMP ROOM FOUNDATION |  |  | FINISHED (AVAILABLE DETAILS)
2023-09-06 | CVH | TA JUMP 04 ACS (CJ BETWEEN GF AND L01)
2023-09-07 | CVH | TA JUMP 04 ACS (CJ BETWEEN GF AND L01) |  |  | 70% COMPLETED
| SHOBHA ONE | PILECAP PC 103 SUBMISSION | 535.4 | 7 | SUBMITTED
|  | PILECAP PC 70A SUBMISSION | 314.65 | 6
2023-09-08 | CVH | TA JUMP 04 ACS (CJ BETWEEN GF AND L01)
2023-09-09 | CVH | TA JUMP 04 ACS (CJ BETWEEN GF AND L01) |  |  | SUBMITTED FOR CHECKING
| SHOBHA HARTLAND | TYPE C FOUNDATION UPDATION |  |  | SUBMITTED
2023-09-10 | SHOBHA VERDE | WATER TANK AND PUMP ROOM FOUNDATION |  |  | DETAILING COMPLETED,SECTIONS AND UPDATION BASED ON TENDER DRWG
2023-09-11 | AL BARSHA SECOND | L02 TO L03 COREWALL |  |  | SUBMITTED FOR PRI CHECKING
2023-09-12 | SHOBHA HARTLAND | TA FOUNDATION UPDATION FOR COVER CHANGE |  |  | SUBMITTED
| CVH | TA JUMP 04 ACS (CJ BETWEEN GF AND L01 PRIMARY COMMENTS |  |  | SUBMITTED FOR SEC CHECKING
2023-09-13 | CVH | TA JUMP 04 ACS (CJ BETWEEN GF AND L01 SEC COMMENTS & SUBMISSION | 60.39 | 5 | SUBMITTED
| CREST GRANDE | WATER TANK COVER SLAB CONSULTANT COMMENTS |  |  | SUBMITTED
2023-09-14 | SHOBHA VERDE | WATER TANK AND PUMP ROOM FOUNDATION |  |  | 90% COMPLETED
2023-09-15 | G&B | LIFT CORE WALL REINF DETAILS TOWER B
2023-09-16 | SANGYONG | LIFT CORE 1 REINF DETAILS | 40.16 | 1
2023-09-17 | SUNDAY
2023-09-18 | LEAVE
2023-09-19 | CREST GRANDE | L37 SLAB POUR1 AND 2 UPDATION | 4.595 | 1
|  |  | 5.82 | 1
2023-09-20 | SHOBHA VERDE | FOUNDATION REINF DETAILS COMMENTS
2023-09-21 | CVH | PC168 UPDATION BASED ON LATEST IFC (DRAIN AND SUMP PIT)
2023-09-22 | CVH | PC168 UPDATION BASED ON LATEST IFC (DRAIN AND SUMP PIT) |  | 1 | SUBMITTED
2023-09-23 | SHOBHA VERDE | FOUNDATION REINF DETAILS | 951.54 | 14
2023-09-24 | SUNDAY
2023-09-25 | SHOBHA MOSQUE | FOUNDATION REINF DETAILS
| AL BARSHA SECND | L02 TO L03 COREWALL SUBMISSION | 16.59 | 2 | SUBMITTED
2023-09-26 | SHOBHA HARTLAND | TYPE A&C FOUNDATION UPDATION AS PER LATEST IFC
2023-09-27 | AL BARSHA SECND | L03 TO L04 COREWALL
| SHOBHA MOSQUE | FOUNDATION B1
2023-09-28 | SHOBHA MOSQUE | FOUNDATION B1 LAYER
2023-09-28 | SHOBHA HARTLAND | TYPE AFOUNDATION UPDATION AS PER LATEST IFC
| SHOBHA RESERVE | VVILLA 4A FOUNDATION B1 |  |  | JUST STARTED
2023-09-29 | SHOBHA MOSQUE | FOUNDATION RAFT COMMENTS | 12.295 | 1 | SUBMITTED
|  | TOTAL | 1951.631 | 41

## OCT
DAILY REPORT ( SEPT-OCT 2023)
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2023-10-01 | SUNDAY
2023-10-02 | SHOBHA MOSQUE | COMMENTS FROM NSR
| G&B | L03 TO L05 TYPICAL COREWALL |  |  | SUBMITTED FOR CHECKING
2023-10-03 | CREST GRANDE | TOWER B PODIUM POUR 15 UPDATION
| SHOBHA VERDE | FOUNDATION COMMENTS
2023-10-04 | G&B | L03 TO L05 TYPICAL COREWALL COMMENTS AND SUBMISSION | 16.34 | 2
| SHOBHA VERDE | FOUNDATION COMMENTS
2023-10-05 | SHOBHA VERDE | FOUNDATION COMMENTS |  | 2 | SUBMITTED
2023-10-06 | CVH | TB PC149 STARTER UPDATION LATEST IFC
TB NON ACS UPDATION FOUNDATION TO GF
2023-10-07
2023-10-08 | SUNDAY
2023-10-09 | CVH | TB NON ACS UPDATION FOUNDATION TO GF |  |  | SUBMITTED
2023-10-10 | ABSENT
2023-10-11 | SHOBHA MOSQUE | FOUNDATION UPDATION TRENCH |  |  | SUBMITTED
| CREST GRANDE RAMP BEAM UPDATION GF TO L1 AND L1 TO L2 |  |  |  | SUBMITTED
2023-10-12 | CREST GRANDE RAMP BEAM UPDATION GF TO L1 AND L1 TO L2 | RAMP SLAB UPDATION |  | 2
|  | GF TO L1 COLUMNS POUR 15 | 1.486 | 0.5
|  | RAMP-02 BEAM GF TO L1 | 7.872 | 1.3
2023-10-13 | CREST GRANDE | L1 TO L2 RAMP BEAM
| CVG | L43 SLAB UPDATION |  |  | SUBMITTED
2023-10-14 | CREST GRANDE | L1 TO L2 RAMP-02 BEAM AND SLAB | 26.37 | 3 | SUBMITTED FOR CHECKING
2023-10-15 | SUNDAY
2023-10-16 | CREST GRANDE | L2 TO L3 RAMP-02 BEAMS
| CVH | TA PC168 UPDATION FOR LATEST IFC REV 2
2023-10-17 | SHOBHA ONE | PC70 A UPDATION BASED ON LATEST IFC
| SHOBHA MOSQUE | TOWER CRANE FOUNDATION | 2.74 | 1
| G&B | L01 SLAB COMMENTS
| CVH | TA PC168 UPDATION FOR LATEST IFC REV 2
2023-10-18 | SHOBHA VERDE | FOUNDATION UPDATION FOR LAP AND LATEST IFC
2023-10-19 | SHOBHA VERDE | FOUNDATION UPDATION FOR LAP AND LATEST IFC |  |  | SUBMITTED
| SHOBHA VERDE | FOUNDATION STARTER COMMENTS
2023-10-20 | SHOBHA VERDE | FOUNDATION RETAINING WALL STARTERS | 17.67 | 3 | SUBMITTED
2023-10-21 | SHOBHA VERDE | TOWER CRANE FOUNDATION | 4.93 | 1
| SHOBHA ONE | TOWER CRANE FOUNDATION | 25.67 | 1
| CREST GRANDE | RAMP BEAM UPDATION RAMP 01 GF TO L0Q |  | 1
2023-10-22 | SHOBHA ONE | L07 SLAB MESH
2023-10-23 | CVH | PODIUM PILECAP UPDATION
| SHOBHA ONE | L07 SLAB MESH
| SHOBHA HARTLAND | TA FOUNDATION CONSULTANT COMMENTS
2023-10-24 | SHOBHA RESERVE | VILLA TYPE 4A M FOUNDATION REINF DETAILS | 9.61 | 3 | SUBMITTED FOR CHECKING
2023-10-25 | SHOBHA ONE | PC 61 AND 103 UPDATION AS PER LATEST IFC |  |  | SUBMITTED
2023-10-28 | SHOBHA MOSQUE | consultant comments foundation
| DHOBHA RESERVE | VILLA 4A M FOUNDATION |  |  | SUBMITTED
2023-10-28
2023-10-30 | CREST GRANDE | RAMP 02 L1 TO L2 UPDATION |  |  | SUBMITTED
2023-10-31 | SHOBHA VERDE | PILECAP UPDATION BASED ON LATEST SUMP PIT
|  | TOTAL | 112.688 | 20.8

## NOV
DAILY REPORT (OCT-NOV 2023)
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2023-10-26 | SHOBHA VERDE | PILECAP UPDATION |  |  | SUBMITTED
| CREST GRANDE | L1 to L2 RAMP BEAM UPDATION
2023-10-27 | SHOBHA MOSQUE | FOUNDATION UPDATION AS PER LATEST GA
| CREST GRANDE | L2 TO L3 RAMP 02 BEAMS
2023-10-28 | CREST GRANDE | RAMP BEAM SITE COMMENTS RAMP02 L1 TO L2
2023-10-29 | SHOBHA MOSQUE | FOUNDATION UPDATIOM BASED ON LATEST IFC
2023-10-30
2023-10-31
2023-11-01
2023-11-02
2023-11-03
2023-11-04
2023-11-05
2023-11-06
2023-11-07
2023-11-08
2023-11-09
2023-11-10
2023-11-11
2023-11-12
2023-11-13
2023-11-14
2023-11-15
2023-11-16
2023-11-17
2023-11-18
2023-11-19
2023-11-20
2023-11-21
2023-11-22
2023-11-23
2023-11-24
2023-11-25
|  | TOTAL | 0 | 0

## DEC
DAILY REPORT (NOV-DEC 2023)
DATE | CUST/PROJECT | DESCRIPTION | WT/MT | NO OF SHEETS | REMARKS
2023-11-26
2023-11-27
2023-11-28
2023-11-29
2023-11-30
2023-12-01
2023-12-02
2023-12-03
2023-12-04
2023-12-05
2023-12-06
2023-12-07
2023-12-08
2023-12-09
2023-12-10
2023-12-11
2023-12-12
2023-12-13
2023-12-14
2023-12-15
2023-12-16
2023-12-17
2023-12-18
2023-12-19
2023-12-20
2023-12-21
2023-12-22
2023-12-23
2023-12-24
2023-12-25
|  | TOTAL | 0 | 0